# SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

This file is a fictional training example. Not an official record.

## CCTV Pilot Implementation Report

Document ID: SYN-PDY-CCTV-001-IMPLEMENTATION-003

Proposal ID: SYN-PDY-CCTV-001

SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

IMPLEMENTATION REPORT

Proposal ID: SYN-PDY-CCTV-001

Report Date: 2024-06-15

STATUS: COMPLETED

IMPLEMENTATION TIMELINE:

- Tender Issued: Feb 12, 2024

- Vendor Selected: Mar 05, 2024 (fictional vendor for demo)

- Installation Started: Mar 22, 2024

- Installation Completed: May 10, 2024

- Testing & Training: May 11-25, 2024

- Final Acceptance: June 01, 2024

ACTUAL COST: INR 4,45,000 (under budget by INR 5,000)

DEVIATIONS FROM PLAN:

- Installation completed 10 days ahead of schedule

- Minor layout adjustment required for camera placement

- Additional training session conducted at team request

CHALLENGES FACED:

1. Network connectivity issues resolved by IT team

2. Power backup capacity verified and upgraded

3. Camera angle adjustments for optimal coverage

TRAINING COMPLETED:

- 12 personnel trained on system operation

- User manual provided in English and local language

- Emergency procedures documented

HANDOVER STATUS:

- System operational since June 01, 2024

- Vendor support available for warranty period

- Maintenance schedule established

This is a SYNTHETIC implementation report for demonstration purposes only.