# SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

This file is a fictional training example. Not an official record.

## CCTV Pilot Outcome Assessment

Document ID: SYN-PDY-CCTV-001-OUTCOME-004

Proposal ID: SYN-PDY-CCTV-001

SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

OUTCOME ASSESSMENT REPORT

Proposal ID: SYN-PDY-CCTV-001

Assessment Date: 2024-09-15

Assessment Period: June 01 - Sept 15, 2024 (3.5 months)

OUTCOME: SUCCESSFUL

PERFORMANCE METRICS:

- System Uptime: 99.2%

- Incidents Documented: 45 (all successfully recorded)

- Storage Utilization: Optimal (28-day retention maintained)

- Staff Satisfaction: 4.2/5 (based on feedback survey)

BENEFITS REALIZED:

1. Enhanced Security Monitoring

- Comprehensive coverage of entry/exit points

- Successful documentation of all incidents

- Improved response time to security events

2. Operational Improvements

- Visual verification of activities

- Evidence for incident investigations

- Deterrent effect observed

3. Training Value

- Team gained expertise in CCTV operations

- Best practices identified for future expansion

- Maintenance procedures established

LESSONS LEARNED:

1. Adequate network bandwidth is critical

2. Proper lighting improves night vision effectiveness

3. Regular maintenance prevents minor issues

4. User training is essential for optimal utilization

ISSUES ENCOUNTERED:

- Minor technical issue (camera 5 adjustment) resolved within warranty

- One instance of network downtime (resolved in 2 hours)

- Storage management procedures refined

RECOMMENDATIONS FOR EXPANSION:

1. Similar systems suitable for Demo North and Demo South stations

2. Budget estimate: INR 4,50,000 to 5,00,000 per station

3. Consider centralized monitoring for multiple locations

4. Include redundancy for critical camera positions

MAINTENANCE STATUS:

- Regular cleaning schedule established

- Vendor support responsive during warranty period

- Maintenance contract renewal under consideration

This is a SYNTHETIC outcome report for demonstration purposes only.