# SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

This file is a fictional training example. Not an official record.

## Initial CCTV Pilot Proposal

Document ID: SYN-PDY-CCTV-001-PROPOSAL-001

Proposal ID: SYN-PDY-CCTV-001

SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

PROPOSAL FOR CCTV SURVEILLANCE PILOT PROJECT

Proposal ID: SYN-PDY-CCTV-001

Station: Demo Central Station

Date: 2024-01-15

OBJECTIVE:

Install a pilot CCTV surveillance system at Demo Central Station to enhance security monitoring and improve incident response capabilities.

SCOPE:

- 8 IP-based cameras covering entry, exit, and critical areas

- Network Video Recorder (NVR) with 2TB storage (30-day retention)

- Centralized monitoring station

- 24/7 recording capability

TECHNICAL SPECIFICATIONS:

- Camera Resolution: 1080p minimum

- Night Vision: IR range 30 meters

- Network: PoE-enabled for simplified cabling

- Storage: H.265 compression for efficient space utilization

BUDGET:

Total Estimated Cost: INR 4,50,000 (Four Lakh Fifty Thousand)

Breakdown:

- Cameras (8 units @ INR 15,000): INR 1,20,000

- NVR System: INR 80,000

- Installation & Cabling: INR 1,20,000

- UPS & Power Backup: INR 40,000

- Maintenance Contract (1 year): INR 50,000

- Contingency (10%): INR 40,000

TIMELINE:

- Procurement: 1 month

- Installation: 2 months

- Testing & Training: 2 weeks

- Warranty Period: 3 months post-installation

EXPECTED OUTCOMES:

- Comprehensive visual coverage of station premises

- Improved incident documentation

- Enhanced deterrent effect

- Training ground for future CCTV expansion

PROCUREMENT METHOD:

Limited Tender (3 vendors)

This is a SYNTHETIC proposal for demonstration purposes only.