# SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

This file is a fictional training example. Not an official record.

## CCTV Expansion Review Observations

Document ID: SYN-PDY-CCTV-002-REVIEW-006

Proposal ID: SYN-PDY-CCTV-002

SYNTHETIC DEMO DATA - NOT AN OFFICIAL GOVERNMENT RECORD

REVIEW OBSERVATIONS

Proposal ID: SYN-PDY-CCTV-002

Review Date: 2024-10-20

REVIEW STATUS: COMPREHENSIVE REVIEW COMPLETED

TECHNICAL REVIEW:

✓ Specifications match proven pilot system

✓ Vendor market has capacity for multi-site deployment

✓ Timeline is realistic

✓ Quantity estimate appears appropriate

BUDGET REVIEW:

⚠ CONCERN: Total cost (INR 11,00,000) exceeds available budget

✓ Per-station estimate is reasonable (matches pilot adjusted for scale)

⚠ Current fiscal year allocation: INR 6,00,000 remaining

⚠ Next fiscal year budget not yet approved

OPERATIONAL REVIEW:

✓ Both stations have expressed need for CCTV coverage

✓ Network infrastructure being assessed at both locations

⚠ Demo South Station may need network upgrades (estimated INR 50,000)

✓ Staff training can leverage pilot project experience

PROCUREMENT REVIEW:

✓ Open tender is appropriate for this scale

✓ Market competition expected to be good

✓ Pilot vendor performance can be considered

✓ No procurement obstacles identified

RISK ASSESSMENT:

1. Budget Constraint (High Risk)

- Mitigation: Consider phased approach

2. Network Infrastructure (Medium Risk)

- Mitigation: Include network assessment in tender

3. Multi-site Coordination (Medium Risk)

- Mitigation: Staggered deployment schedule

REVIEWER QUESTIONS:

1. Can deployment be phased? (One station now, one later)

2. What is priority ranking between the two stations?

3. Can network upgrade cost be sourced separately?

4. Is centralized monitoring essential or optional?

RECOMMENDATION:

DEFER pending budget availability.

Alternative Options:

A. Implement Demo North Station only (INR 5,50,000) in current FY

B. Defer both stations to next FY when full budget may be available

C. Scale down to pilot-size systems (8 cameras each) to reduce cost

NEXT STEPS REQUIRED:

- Budget allocation confirmation

- Station priority determination

- Network infrastructure assessment results

- Revised proposal if phased approach is selected

This is a SYNTHETIC review document for demonstration purposes only.